BIKE SHORTS FESTIVAL 2008 TASK LIST

Compiled April 2, 2008

Content

- Await remaining content to arrive

- The review

- Set up play lists

Venue

- Preview parking – confirm with land lord location and set up time

- Preview projection equipment and PA

- Preview lobby for VACC tables and other displays

Website

- Content determined

- Ginny’s needs taken care of

Parking

- Confirmation from VACC that racks and volunteers are confirmed

- Let VACC take care of all things parking

Presales

- Tickets or system distributed to participating shops

- Ticket sale tracking system implemented

Promotions

- Flyers/posters designed and printed

- Flyers/posters distributed

  - Bike shops (which ones and when?)

  - Bike friendly businesses

Evening

6:00 to 6:15 - Set up

6:15 to 6:30 - People will start to arrive (400 of them)

6:30 to 7:15 - First half

7:15 to 8:00 - Intermission/ Awards/ 50/50 draw

8:00 to 8:40 - Second half

8:40 to 9:00 - People meander casually out of the theatre

9:00 - Bike racks strike